## Tabelle1
Sprint Review Protocol
Sprint No: |  | 1
Date & Time |  | 2022-10-18 15:00
Group Number |  | 22+23
Participant 1 |  | Taha Samaha
Participant 2 |  | Jan Loos
Participant 3 |  | Fatema Aly
Participant 4 |  | Alexander Kramreiter
Participant 5
Mentor |  | Dipl.-Ing. Bernhard Wallisch
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
1 | Espresso-IT Introduction | 1.5 | 1.5 | 0 |  |  | Zoom Meeting with Mentor
2 | Espresso-IT Local Setup | 3 | 4 | 1 |  |  | Deployed via Docker
3 |  |  |  | 0
4 |  |  |  | 0
5 |  |  |  | 0
6 |  |  |  | 0
7 |  |  |  | 0
… |  |  |  | 0
… |  |  |  | 0
n |  |  |  | 0
7 |  |  |  | 1 | 0 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol