## Tabelle1
Sprint Review Protocol
Sprint No: |  | 4
Date & Time |  | 2022-12-06 18:00
Group Number |  | 22+23
Participant 1 |  | Taha Samaha
Participant 2 |  | Jan Loos
Participant 3 |  | Fatema Aly
Participant 4 |  | Alexander Kramreiter
Participant 5
Mentor |  | Dipl.-Ing. Bernhard Wallisch
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
1 | Team Meeting | 1.5 | 1.5 | 0 |  |  | Team
2 | tool.py and run.py | 3 | 3 | 0 |  |  | Jan Loos
3 | Docker Configuration | 5 | 5 | 0 |  |  | Taha Samaha
4 | Java Runfile (50%) | 3 | 3 | 0 |  |  | Fatema Aly
5 | Project Diary | 1 | 1 | 0 |  |  | Team
6 |  |  |  | 0
7 |  |  |  | 0
… |  |  |  | 0
… |  |  |  | 0
n |  |  |  | 0
7 |  |  |  | 0 | 0 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol